## Sheet1
S.No | Date | Bug/Corrections/New Requirement | Template | Level | Role | Change | Priority | Status | Assigned To | Closed Date
1 | 2026-06-21 | Request statstics alignments in correct due to Headings | Dashboard | Admin | All | Cosmetic | High | Open
2 | 2026-06-21 | Commission amount tab : Under line text (Pay-in + pay-out fees), change to (Pay In + Pay Out Fees) | Dashboard | Admin | Admin | Cosmetic | High | Open
3 | 2026-06-21 | Net Amount tab : Gross - Commission ? Which Gross | Dashboard | Admin | Admin | Cosmetic | High | Open
4 | 2026-06-21 | Deposits, Withdrawals,Settlements headings keep in Black color like above containers | Dashboard | Admin | Admin | Cosmetic | High | Open
5 | 2026-06-21 | Deposits, Withdrawals,Settlements container | [5 empty] | Open
6 | 2026-06-21 | Change Member ID to Membership Number | All | Admin,Merchant | Deposit Operator,Admin | Cosmetic | High | Open
7 | 2026-06-21 | Copy function for Reference numbers | All | Admin,Merchant | All | Function | High | Open
8 | 2026-06-21 | Sending account details capture at all deposit modes | Deposit Management | Merchant | Deposit Operatpor | Function | High | Open
9 | 2026-06-21 | Audit Log View : Button under Action for all completed transactions | Deposit, Withdrawal,Settlement | Merchant | Manager | New | High | Open
10 | 2026-06-21 | Multiple Users Control : Opened, action button disable to other user to perform next step | Deposit, Withdrawal,Settlement | Merchant | Except Manager | New | High | Open
11 | 2026-06-21 | Allow multiple slips upload | Deposit Management | Merchant | Deposit Operator, Data Operator | New | High | Open
12 | 2026-06-21 | Multiple modes accepted for withdrawals |  | Merchant |  | New | High | Open
13 | 2026-06-21 | Individual URL's for admin and merchant | System | Admin,Merchant | All | New | High | Open
14 | 2026-06-21 | Request under in Dashboard all types filtering values, remove unwanted | Dashboard | Merchant | All | Function | High | Open
15 | 2026-06-21 | Login Landing page | System | Merchant | All | Display | High | Open
16 | 2026-06-21 | Implement New Logo | System | Admin,Merchant | All | Display | High | Open
17 | 2026-06-21 | Search : By all values, Date Ranges | All Transactions | Admin,Merchant | All | Function | High | Open
18 | 2026-06-21 | Deposit account image generation | Deposit Management | Merchant | Deposit Operator, Data Operator | Function | High | Open
19 | 2026-06-21 | Withdrawal addition to pending status of withdrawal request | Withdrawal Management | Merchant | Withdrawal Operator, Data Operator | New | High | Open
20 | 2026-06-21 | Live support sub window right corner bottom, not full screen | All | Merchant | All | Change | High | Open